## Sheet1
Job's Daughters International
Strategic Plan | Updated June 2018
Strategic Task | Responsible Sub Group | Committee Review | Status | Recommended Target Dates | Completed Steps
Strategic Objective | Leadership and People
Strategic Goal | Operate a highly effective and efficient organization dedicated to the growth and support of our Bethels, JGC, GGC, Alumni, International Office & SGC
Develop training modules that teach a consistent method for use of required materials | Training Development Group | Leadership Committee | In Process | 2017-2019 | Completed the PowerPoint for "Annual Report" training and posted on the Supreme Website Completed the "Welcome Booklet" for Daughters and posted on the Supreme Website
Identify the required materials used in each council members position | Training Development Group Lead Coordinator: Sheila Gavin | Leadership Committee | In Process | 2017-2018
Bethel Guardian
Associate Bethel Guardian
Guardian Secretary
Guardian Treasurer
(Guardian) Director of Music
(Guardian) Director of Epochs
Custodian of Paraphernalia
Promoter of Finance
Promoter of Socialbility
Promoter of Hospitality
Promoter of Youth Activities
Promoter of Good Will
Promoter of Fraternal Relations
Director of Promotion
Director of Patrol
Rework and streamline the constitution and bylaws | Strategic Planning Implementation Group | Jurisprudence Committee | In Process | 2016-2021
Reformat the current Constitution & Bylaws | Strategic Planning Implementation Group | Jurisprudence Committee | Completed | N/A | The reformatted Constitution and Bylaws were approved by the body at the 2016 Supreme Session and publiished later that year.
Supreme Constituion & Bylaws - Applicable to BUS | Strategic Planning Implementation Group | Jurisprudence Committee | Completed | N/A | Once the new reformatted law was published, all juristidications under Supreme were now in compliance.
Grand Guardian Councils - Applicable to each Jurisdiction | Strategic Planning Implementation Group | Jurisprudence Committee | In Process | 2017-2019
Phase 1 - All US, Canada | Strategic Planning Implementation Group | Jurisprudence Committee | In Process | 2017-2018
Phase 2 - Phillipines, Brazil | Strategic Planning Implementation Group | Jurisprudence Committee | In Process | 2018-2019
Jurisdictional Guardian Councils - Applicable to each Jurisdiction | Strategic Planning Implementation Group | Jurisprudence Committee | In Process | 2017-2019
Bethels Bylaws - Applicable to each Bethel in the Organization | Strategic Planning Implementation Group | Jurisprudence Committee | Not Started | 2019-2020
Streamline the Bethel & Bethel Guardian Council Constitution/Bylaws/SOP Sections of the Constitution & Bylaws | Bylaw Review Group: Lead Coordinator: Melinda Kinders | Jurisprudence Committee | In Process | 2018-2019
Streamline the Grand & Jurisdictional Guardian Council Constitution/Bylaws/SOP sections of the Constitution & Bylaws | Bylaw Review Group | Jurisprudence Committee | Not Started | 2020-2021
Streamline the Supreme Guardian Council Constitution/Bylaws/SOP Sections of the Constitution & Bylaws | Bylaw Review Group | Jurisprudence Committee | Not Started | 2019-2020
Determine if the geographical structure of the jurisdictions should be determined by other than political or state, province boundaries | Jurisprudence Committee Darrell Vierling | Jurisprudence Committee | Not Started | TBD
Strategic Objective | Operational Efficiency
Strategic Goal | Provide our members/customers and Bethels with appropriate support, in a timely manner at reasonable and responsible costs
Develop an online access to the directory that is password protected | Leadership Committee | Leadership Committee | Completed | N/A | Directory can be found on the Supreme Website
Develop online job responsibilities training for council positions | Training Development Group | Leadership Committee | In Process | TBD | Completed the PowerPoint for "Annual Report" training and posted on the Supreme Website Training Development Group to meet and determine timelines
Bethel Guardian Council Duties | Training Development Group | Leadership Committee | In Process
Paperwork required for Regular Meeting | Training Development Group | Leadership Committee | In Process
Paperwork required for Initiation Meeting | Training Development Group | Leadership Committee | In Process
Other Forms Used | Training Development Group | Leadership Committee | Not Started
Financial Books | Training Development Group | Leadership Committee | Not Started
How to write a Grant Application | Training Development Group | Leadership Committee | Not Started
How to complete the Annual Report (Form 110) | Training Development Group | Leadership Committee | Completed | N/A | Posted on the Supreme Website November 2016
Develop Daughter Training Modules | Training Development Group | Leadership Committee | In Process | 2018-2019 | Completed the "Welcome Booklet" for Daughters and posted on the Supreme Website
Welcome to JDI | Training Development Group | Leadership Committee | Completed | N/A | Posted on the Supreme Website November 2016
Term Planning | Training Development Group | Leadership Committee | In Process | 2018-07-01
Fundraising/Activity Planning | Training Development Group | Leadership Committee | In Process | 2018-07-18
Understanding Parliamentary Procedure | Training Development Group | Leadership Committee | Not Started | 2019-04-01
Being a Jobie Leader | Training Development Group | Leadership Committee | Not Started | 2019-04-01
Develop an make available an ebook version of the ritual, music ritual, and supreme book of ceremonies | Board of Trustees | Board of Trustees | Completed | TBD
Ritual - English version | Board of Trustees | Board of Trustees | Completed | N/A | eRitual is available from Barnes & Noble and Amazon for Nook and Kindle users
Ritual - Portugese version | Board of Trustees | Board of Trustees | Completed
Music Ritual | Board of Trustees | Board of Trustees | Removed | N/A
Supreme Book of Ceremonies - English version | Board of Trustees | Board of Trustees | Completed | TBD
Supreme Book of Ceremonies - Portugese version | Board of Trustees | Board of Trustees | Completed | TBD
Establish an internship project to develop a new website that includes a membership database, current members, adult volunteers, and alumni | Board of Trustees | Board of Trustees | In Process | TBD
New Website | Board of Trustees | Board of Trustees | Completed | N/A | New website was launched in 2017
Membership Database | Board of Trustees | Board of Trustees | In process | TBD
Develop succession plan for Executive Manager, Office Staff, and Leadership Roles | Executive Manager | Board of Trustees | In Process | Ongoing
Executive Manager | Executive Manager | Board of Trustees | In Process | Ongoing
Office Staff | Executive Manager | Board of Trustees | In Process | Ongoing
Leadership Roles | Executive Manager | Board of Trustees | In Process | Ongoing
Develop a maintenance and operations plan regarding the Supreme Office Maintenance | Executive Manager Executive SGC | Board of Trustees | Completed | TBD
Identify what is currently in place, assess for future needs, and implement | Executive Manager Executive SGC | Board of Trustees | Completed | TBD
Current Status | Executive Manager Executive SGC | Board of Trustees | Completed | TBD
Future Status | Executive Manager Executive SGC | Board of Trustees | Completed | TBD
Implementation of Plan | Executive Manager Executive SGC | Board of Trustees | In Process | Ongoing
Member/Customers
Provide our members/customers with a positive growth experience that exceeds expectations, consistently delivers and supports relevant programs and training
Create educational delivery system | Board of Trustees | Board of Trustees | In Process | 2017-2018
Develop a coordinated delivery system for education programs working with other pillars | Board of Trustees | Board of Trustees | In Process | TBD
Create strategic planning platforms | Strategic Planning Implementation Group | Board of Trustees | In Process | TBD
Investigate Plug and Play programs | Strategic Planning Implementation Group | Board of Trustees | In Process | TBD
Educate the GGCs and JGCs regarding strategic planning process | Strategic Planning Implementation Group | Board of Trustees | In Process | No End
Determine relevance of current programs, supreme committees (Supreme Programs) | Executive SGC | Board of Trustees | In process | TBD
Restructure Spirit Award Program | Executive SGC | Executive SGC | In Process | Ongoing
Create #JDI Program | Executive SGC | Executive SGC | Completed | 2017-2018
Are the current programs meeting the Strategic Initiative | Executive SGC | Executive SGC | In Process | TBD
Identify and collect existing training programs | Executive SGC | Executive SGC | In Process | TBD
Assess the above for relevance | Executive SGC | Executive SGC | In Process | TBD
Financial Sustainability
Establish realistic budgets that provide services to our members, support to our Bethels, and appropriate governance to the organization, developing initiatives that continue to increase revenue, manage expenses and develop long term financial stability
Review and assess the efficiency of the current budget process | Finance Committee | Board of Trustees | Completed
Develop a budgetary process that meets the needs of the organization | Board of Trustees | Board of Trustees | In Process
Educate responsible parties on the financial reporting process | Board of Trustees Finance Committee | Board of Trustees | In Process
Identify the needs of the line to facilitate planning | Board of Trustees | Board of Trustees | in Process
Involve addiitonal parties as needed | Board of Trustees | Board of Trustees | in Process
Develop a financial reporting process that is understandable and transparent | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process
identify "what we are using currently" | Executive Manager Board of Trustees Finance Committee | Board of Trustees | Completed | N/A
Identify the needs, create a proposal, and update as approved | Executive Manager Board of Trustees Finance Committee | Board of Trustees | Completed | Ongoing | Recommendations were presented to the BOT in August 2015
Implementation of Plan | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | Ongoing
Develop process to educate "Stakeholders" regarding the financial position of the organization | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | 2017-2018
Identify current reporting process | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | TBD
Define a process of what do we need to communicate and how do we communicate that | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | TBD
Develop a Financial Disaster Recovery Plan (i.e.: lawsuit/financial crash) | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | TBD
Identify current, update, and develop as needed, implement | Executive Manager Board of Trustees Finance Committee | Board of Trustees | In Process | TBD
Growth and Innovation
Providing relevant, up to date benefits, programs, and products to exceed our members/customers expectations
Create a communication Plan to offer feedback and discussion in a safe environment | Supreme Promotion Committee | Board of Trustees | In Process
Investigate methods of including more voices in the legislative process at Supreme Session | Strategic Planning Implementation Group | Board of Trustees | In Process | Ongoing
Evolve Supreme Session into Developmental Conference | Leadership Committee Supreme Arrangements Committees | Executive SGC | In Process | Ongoing